## Details of ongoing projects
DETAILS OF ONGOING PROJECTS (RS. IN CRORES).
Sl. No. | State | Name of Project Construction of school building, staff quarters, boundary wall etc of KV | Cost of Project (Rs. In Crore) | Amount already spent (Rs. In Crore) | Amount already spent | Balance amount required (Rs. In Crore) | Finance (Rs. In Crore) | Date of completion | Present status/ Physical progress as on date
1 | Andhra Pradesh | Tenali | 16.01 | 14.2 | 14.2 | 1.81 | 1.81 | March, 2019 | 79%
2 | Chhattisgarh | Narayanpur | 16.94 | 4.2 | 4.2 | 12.74 | 12.74 | June, 2019 | 40%
3 | Chhattisgarh | Hasaud,Janjgir | 15.97 | 12.2 | 12.2 | 3.77 | 3.77 | Nov, 2018 | 95%
4 | Himachal Pradesh | Saloh | 16.21 | 0 | 0 | 16.21 | 16.21 | March, 2021 | Yet to start
5 | Karnataka | Chikodi | 17.11 | 6.2 | 6.2 | 10.91 | 10.91 | Oct., 2019 | 22%
6 | Odisha | No.2 Sambalpur | 16.46 | 2.2 | 2.2 | 14.26 | 14.26 | March, 2019 | 50%
7 | Rajasthan | Hanumangarh | 16.05 | 8.2 | 8.2 | 7.85 | 7.85 | March, 2019 | 83%
8 | Telangana | Miryalaguda | 15.25 | 10.2 | 10.2 | 5.05 | 5.05 | March, 2019 | 63%
9 | Telangana | Sirsilla | 16.52 | 0 | 0 | 16.52 | 16.52 | March, 2021 | Yet to start
10 | Uttar Pradesh | Sharawasti | 15.85 | 0.2 | 0.2 | 15.65 | 15.65 | March, 2021 | 4%
11 | Uttar Pradesh | Gangrani | 16.81 | 0.2 | 0.2 | 16.61 | 16.61 | March, 2021 | Yet to start
|  |  | 179.18 | 57.8 | 57.8 | 121.38 | 121.38
15.10.2018